## Start Here
CARLOS J. MOLINA · GRC CONSULTING
Gap Tracker
Custody Corp · SMCTR Framework — Bridge: Map → Test · v1.0
WHAT THIS IS
The 65 Annex A controls identified in the Custody Corp Statement of Applicability that are not yet fully Implemented (Not started or Partially implemented), organized as individual remediation items with an owner, a priority, and a target date.
HOW TO USE IT
1. Priority reflects the security target ratings of the assets each control protects and its role in the risk scenarios already assessed (R.01–R.03) — not a generic checklist weighting.
2. Every row needs a Remediation owner before target dates are set. An item without an owner does not get worked.
3. Target dates are intentionally left blank in this version — they belong to a remediation planning conversation with the risk owner, not to the diagnostic phase this tracker was built in.
4. Gap description is drawn directly from the corresponding row of the Statement of Applicability — this tracker does not re-analyze anything, it re-packages the SoA findings for follow-up.
SOURCE
Derived from the Custody Corp Statement of Applicability (ISO/IEC 27001:2022 Annex A). Column structure inspired by common GRC gap-tracking conventions; control titles, gap descriptions, and prioritization are original work for this engagement.

## Gap Tracker
Annex A Ref | Domain | Control | Implementation Status | Gap Description | Priority | Remediation Owner | Target Date | Notes
A.5.1 | Organizational | Information security policy framework | Not started | No formal, documented information security policy exists. Practices identified throughout this assessment (password requirements, backup routines, physical security measures) operate informally, without a governing policy framework. | Medium | Vice Presidency
A.5.2 | Organizational | Security roles and responsibilities | Partially implemented | The IT lead assumes information security responsibilities by default, without any formal designation, documented role description, or defined authority specific to information security. | Medium | Vice Presidency
A.5.4 | Organizational | Management enforcement of security expectations | Not started | No formal communication from leadership reinforces information security expectations to staff. | Medium | Vice Presidency
A.5.5 | Organizational | Contact with authorities | Not started | No procedure or established contact with relevant authorities exists for situations that may require it. | Low | Vice Presidency
A.5.6 | Organizational | Contact with industry peers and law enforcement | Partially implemented | Informal information-sharing relationships exist with other companies in the security sector and with law enforcement organizations. No formal membership, structured channel, or documented arrangement exists. | Low | Vice Presidency
A.5.7 | Organizational | Use of threat intelligence | Partially implemented | Threat-relevant information obtained through informal relationships with sector peers and law enforcement (see A.5.6) is used to inform general security decisions. No formal threat intelligence process, source evaluation, or structured analysis exists. | Low | Vice Presidency
A.5.8 | Organizational | Security consideration in project decisions | Partially implemented | Information security risk is considered when undertaking system-related projects — evaluations were performed informally when the Payroll and Administrative Systems were implemented, and when the Cold Standby Server was deployed. This evaluation is not documented as part of a formal project management methodology. | Medium | Vice Presidency
A.5.10 | Organizational | Acceptable use of assets | Partially implemented | Acceptable use expectations exist and are communicated verbally at the start of the employment relationship. No written, formalized acceptable use policy exists. | Medium | Vice Presidency
A.5.12 | Organizational | Information classification | Partially implemented | Information is handled de facto as confidential, but no formal classification scheme exists, and this expectation is not communicated to personnel. | Medium | Vice Presidency
A.5.13 | Organizational | Information labelling | Not started | No information labelling practice exists, consistent with the absence of a formal classification scheme (A.5.12). | Low | Vice Presidency
A.5.14 | Organizational | Rules for information transfer | Partially implemented | Defined data formats and requirements exist for information transfers, but these are not formalized or documented in writing. | Medium | Vice Presidency
A.5.15 | Organizational | Access control rules | Partially implemented | Access is differentiated by role — operational roles (Administrator, Payroll Manager, Operations Manager) hold modification capability, while Vice Presidency holds read-only access (see System Description, DC3). Formal, documented access control policy is pending. | Medium | Vice Presidency
A.5.16 | Organizational | Identity lifecycle management | Partially implemented | A lightweight process exists: access provisioning and de-provisioning are triggered by an email from the Vice Presidency indicating onboarding or offboarding. This process is informal — not documented as a formal procedure, with no defined SLA between notification and action, no access review cadence, and no audit trail beyond the originating email. Vice Presidency initiates the request but the same role also holds read-only access to both systems (see DC3), which warrants review for segregation of duties. | Medium | Vice Presidency
A.5.17 | Organizational | Authentication credential management | Partially implemented | Strong password requirements are enforced at the operating system level and within both the Payroll and Administrative applications. No formal authentication information management process exists beyond these built-in restrictions — no defined password rotation policy, no multi-factor authentication, and no documented procedure for secure credential issuance, reset, or storage. | Medium | Vice Presidency
A.5.18 | Organizational | Access provisioning and revocation | Partially implemented | Access provisioning and de-provisioning are triggered by an email from the Vice Presidency indicating onboarding or offboarding. This process is informal, with no defined SLA, no access review cadence, and no audit trail beyond the originating email. | Medium | Vice Presidency
A.5.19 | Organizational | Supplier security requirements | Partially implemented | Independent banking transaction validation controls are leveraged as an external containment layer for payroll disbursements (Risk Scenario R.01, Applied Control A.5.19). No formal security assessment or requirement has been established with the administrative software vendor. | Medium | Vice Presidency
A.5.20 | Organizational | Security terms in supplier agreements | Partially implemented | Banking agreements include information security clauses, though these are adhesion contracts where the terms — including security clauses — are set unilaterally by the bank, not negotiated or defined by Custody Corp. No security requirements are established in the agreement with the administrative software vendor. | Medium | Vice Presidency
A.5.21 | Organizational | ICT supply chain oversight | Not started | No evaluation of the administrative software vendor's own supply chain (subcontractors or dependencies) has been conducted. | Medium | Vice Presidency
A.5.22 | Organizational | Ongoing supplier monitoring | Not started | No formal ongoing monitoring or review of supplier performance or security exists after initial engagement. | Medium | Vice Presidency
A.5.24 | Organizational | Incident management planning | Partially implemented | A designated incident responder exists (the IT lead), but incident response is limited to notification — there is no documented incident management plan defining classification, escalation paths, response procedures, or roles beyond the initial point of contact. | Medium | Vice Presidency
A.5.25 | Organizational | Security event classification | Not started | No formal classification or severity assessment process exists for security events. Events are handled and reported without a defined classification framework. | Medium | Vice Presidency
A.5.26 | Organizational | Incident response execution | Partially implemented | The IT lead responds to reported events and produces a post-event report documenting what occurred and the solution applied, communicated to leadership. Response follows the IT lead's judgment rather than a documented response procedure. | Medium | Vice Presidency
A.5.27 | Organizational | Learning from incidents | Partially implemented | Post-event reports document what occurred and how it was resolved, communicated to leadership. It has not been confirmed whether these reports are used systematically to update controls or prevent recurrence, versus serving only as an informational record. | Medium | Vice Presidency
A.5.28 | Organizational | Evidence collection and preservation | Partially implemented | Depending on the nature of the failure, IT collects evidence from the Payroll or Administrative Systems, including evidence related to failures in bank data transfer. This is performed on a case-by-case basis without a documented evidence preservation procedure (e.g., chain of custody, retention requirements for legal or contractual purposes). | Medium | Vice Presidency
A.5.29 | Organizational | Security continuity during disruption | Not started | Security controls (access segregation, authentication) must remain enforced when the Cold Standby Server is active following a primary system failure — not yet formally validated as part of restoration testing under A.5.30 (ETA 2027-02-15). | High | Vice Presidency
A.5.30 | Organizational | ICT continuity readiness | Not started | Formal, documented restoration procedure for the shared cold standby server and associated backup storage, addressing Risk Scenario R.02 (Payroll System Unavailability). | High | Vice Presidency
A.5.34 | Organizational | Privacy and personal data protection | Not started | No specific privacy or personal data protection policy has been formalized, beyond the role-based access restrictions already in place (A.8.3). | High | Vice Presidency
A.5.35 | Organizational | Independent review of the security program | Not started | No independent review of the information security program has been conducted prior to this assessment. | Low | Vice Presidency
A.5.36 | Organizational | Compliance verification | Not started | No compliance verification process exists, consistent with the absence of a formal policy framework (A.5.1). | Low | Vice Presidency
A.5.37 | Organizational | Documented operating procedures | Partially compliant | Operating manuals for the Payroll and Administrative Systems exist and are available to personnel who need them. However, the control description requires version control as part of documented operating procedures, which is not currently in place — manuals are not tracked for versioning. | Medium | Vice Presidency |  | Downgraded from Compliant to Partially compliant during the Statement of Applicability review (see Notes Metodologicas).
A.6.2 | People | Security terms in employment | Not started | Employment contracts are generic and do not include explicit information security responsibilities, confidentiality obligations, or acceptable use requirements. | Medium | Vice Presidency
A.6.3 | People | Security awareness training | Not started | No security awareness training program exists — neither at onboarding nor on a recurring basis. | Low | Vice Presidency
A.6.4 | People | Disciplinary process for security violations | Partially implemented | A general HR disciplinary process exists, but it does not specifically address or distinguish information security policy violations. | Medium | Vice Presidency
A.6.5 | People | Obligations surviving termination or role change | Partially implemented | The offboarding process includes return of assigned equipment. No formal confidentiality or information security obligations are defined as surviving termination or role change beyond asset return. | High | Vice Presidency
A.6.6 | People | Confidentiality agreements | Not started | No confidentiality or non-disclosure agreements are signed by personnel with access to payroll or administrative data. | High | Vice Presidency
A.6.8 | People | Security event reporting channel | Partially implemented | A clear reporting channel exists — security events are reported directly to the IT lead. The channel is informal (not documented as a formal procedure) but functionally clear to staff. | Medium | Vice Presidency
A.7.2 | Physical | Physical entry control | Partially implemented | Third-party entry to the facility is tightly controlled (guard, cameras, alarms, sensors). Entry to the server room specifically relies on a physical lock only, with no additional access control, logging, or restriction distinguishing which internal personnel may enter — no access log exists of who enters the server room or when. | Medium | IT Lead
A.7.3 | Physical | Securing offices and rooms | Partially implemented | The office space is physically divided into several separate rooms, but internal personnel have unrestricted access across all of them during working hours — there is no role-based restriction preventing, for example, Operations staff from freely entering the Payroll office. The server room remains the only space with a distinct access control (locked door, see A.7.2). | Medium | IT Lead
A.7.5 | Physical | Protection against environmental threats | Partially implemented | Fire extinguishers and smoke detectors are in place. No climate/humidity control or environmental monitoring specific to the server room has been confirmed. | Medium | IT Lead
A.7.6 | Physical | Rules for working in secure areas | Not started | No formal rules govern conduct or access within the server room beyond the physical lock (see A.7.2). No documented restrictions on visitors or third parties in the area. | Medium | IT Lead
A.7.7 | Physical | Clear desk and clear screen | Not started | No clear desk or clear screen policy is formalized. Screen lock enforcement via Group Policy Object (GPO) was identified as the intended technical control but has not yet been implemented. | Medium | IT Lead
A.7.10 | Physical | Storage media handling | Not started | No controls exist over removable storage media — no USB port restrictions, and no defined procedure for handling or securely disposing of storage media. | Medium | IT Lead
A.7.13 | Physical | Equipment maintenance | Not started | Equipment maintenance is entirely reactive, performed only when a failure occurs. No preventive maintenance program or schedule exists. | Low | IT Lead
A.7.14 | Physical | Secure equipment disposal | Partially implemented | An informal check for sensitive data is performed before equipment disposal, but no formal, documented secure disposal or data-wiping procedure exists. | Medium | IT Lead
A.8.1 | Technological | Endpoint device management | Partially implemented | Individual controls exist on endpoints (antimalware, host firewall, password requirements — see A.8.5, A.8.7, A.8.20), but no unifying endpoint management policy or standard exists. An attempt was made to implement centralized endpoint management via Group Policy Objects (GPO) but was not completed. | Medium | IT Lead
A.8.2 | Technological | Privileged access governance | Not started | Privileged/administrative accounts exist on both the Payroll Server and Administrative Server, but no formal governance is in place: no documented inventory of privileged accounts, no break-glass procedure defining when and by whom the privileged account may be used, no credential rotation policy, no access logging for privileged sessions, and no segregation between who administers the account and who would authorize its use. | High | IT Lead
A.8.5 | Technological | Secure authentication enforcement | Partially implemented | Strong password requirements are enforced at the operating system level and within both the Payroll and Administrative applications. No multi-factor authentication or formal authentication management process exists. | Medium | IT Lead
A.8.6 | Technological | Capacity management | Not started | Capacity is monitored informally and on an ad hoc basis, without documented records or logs. No formal capacity management process, thresholds, or monitoring tooling currently exist. | High | IT Lead
A.8.8 | Technological | Technical vulnerability management | Partially implemented | Operating system automatic updates are enabled on all servers and workstations, providing baseline patching for OS-level vulnerabilities. No formal vulnerability management process exists beyond this — no vulnerability scanning, no defined remediation SLAs by severity, no tracking of third-party application vulnerabilities, and no visibility into whether updates are actually applied successfully. | Medium | IT Lead
A.8.9 | Technological | Configuration management baseline | Not started | No configuration baseline or standard exists for servers or workstations. Configurations are applied on a case-by-case basis without a documented standard. | High | IT Lead
A.8.10 | Technological | Deletion of information no longer required | Not started | No formal data retention or deletion policy exists for payroll or administrative data, including data belonging to former employees. Data is retained indefinitely by default, with no defined schedule or process for secure deletion. | High | IT Lead
A.8.11 | Technological | Data masking | Not started | No data masking or anonymization techniques are currently applied to payroll or administrative data. | High | IT Lead
A.8.12 | Technological | Prevention of data leakage | Not started | No data loss prevention (DLP) controls are currently in place to detect or prevent unauthorized exfiltration of payroll or administrative data. | High | IT Lead
A.8.13 | Technological | Backup adequacy | Partially implemented | Payroll and Administrative data are backed up daily to dedicated backup storage (Payroll Backup Storage, Administrative Backup Storage). A gap between declared and actual RPO was identified during the Map phase and is pending remediation (see System Description, DC3 and DC9). | High | IT Lead
A.8.14 | Technological | Processing redundancy | Partially implemented | Redundancy is achieved through a shared on-premise cold standby server, capable of hosting either the Payroll or Administrative System in the event of primary server failure (see System Description, DC3; Applied Control A.5.30). | High | IT Lead
A.8.15 | Technological | Logging | Partially implemented | Servers retain default operating system logging. Logs are reviewed only reactively, in response to a known event — there is no proactive or scheduled log review process. | Medium | IT Lead
A.8.16 | Technological | Monitoring for anomalous activity | Not started | No proactive monitoring or early-warning alerting for anomalous or suspicious activity exists. Detection is entirely reactive, dependent on an event becoming visible through other means before logs are reviewed (see A.8.15). | High | IT Lead
A.8.18 | Technological | Control of privileged utility programs | Not started | No inventory or assessment of privileged utility programs has been conducted on the Payroll or Administrative Systems. No tools of this nature are known to exist, but absence of a formal assessment means this has not been verified. | High | IT Lead
A.8.19 | Technological | Software installation control | Partially implemented | Restrictions on who may install software on production servers are communicated verbally, but not documented in writing. | Low | IT Lead
A.8.20 | Technological | Network security | Partially implemented | Windows Firewall is enabled on each individual server and workstation, providing host-level network protection. No dedicated network-level firewall or perimeter security appliance exists beyond the router/hub already covered under A.7.11. Network security relies entirely on host-based controls and functional segmentation (A.8.22). | Medium | IT Lead
A.8.21 | Technological | Security of network services | Not started | No review or hardening of network services has been conducted on the servers. Unnecessary services and insecure protocols have not been identified or disabled. | High | IT Lead
A.8.23 | Technological | Web filtering | Not started | No web filtering controls are in place on workstations or servers. | Low | IT Lead
A.8.24 | Technological | Encryption at rest | Partially implemented | Data in transit is encrypted only during transmission to the bank, via the bank's proprietary application — this is the sole point at which encryption is applied. Data at rest (on Payroll Server, Administrative Server, and both backup storage assets) and data in transit within Custody Corp's internal network (server to workstations) are not currently encrypted. | High | IT Lead
A.8.27 | Technological | Secure architecture principles | Partially implemented | Network architecture reflects secure design principles, specifically the functional segmentation of Administration, Payroll, and Operations network segments (see A.8.22), reducing cross-system exposure by design. | Medium | IT Lead
A.8.32 | Technological | Change management | Not started | Change management applies to operational changes (server updates, access reconfiguration, vendor patch application) even in the absence of internal software development. No formal, documented change management process currently exists. | Medium | IT Lead
A.8.34 | Technological | Protection of systems during audit testing | Partially implemented | Special care is taken to protect production data during testing and audit activities, but this practice is not formally documented. | Low | IT Lead

## Summary
Gap Tracker Summary
Custody Corp · as of 2026-09-16
By Priority
High | 17
Medium | 38
Low | 11
By Domain
Organizational | 30
People | 6
Physical | 8
Technological | 22
By Implementation Status
Not started | 30
Partially implemented | 36
Total gap items | 66